## Slide 1: GROUP 1

## Slide 2: Burgess Steps
Step 1. List the project activities in order of precedence. Add to this listing the duration, early start, and float (slack) values for each activity.
Step 2. Starting with the last activity, schedule it period by period to give the lowest sum of squares of resource requirements for each time unit. If more than one schedule gives the same total sum of squares, then schedule the activity as late as possible to get as much slack as possible in all preceding activities.
Step 3. Holding the last activity fixed, repeat Step 2 on the next to the last activity in the network, taking advantage of any slack that may have been made available to it by the rescheduling in Step 2.
Step 4. Continue Step 3 until the first activity in the list has been considered; this completes the first rescheduling cycle.

## Slide 3: Burgess Steps
Step 5. Carry out additional rescheduling cycles by repeating Steps 2 through 4 until no further reduction in the total sum of squares of resource requirements is possible, noting that only movement of an activity to the right (schedule later) is permissible under this scheme.
Step 6. If this resource is particularly critical, repeat Steps 1 through 5 on a different ordering of the activities. which, of course, must still list the activities in order of precedence.
Step 7. Choose the best schedule of those obtained in Steps 5 and 6.
Step 8. Make final adjustments to the schedule chosen in Step 7, taking into account factors not considered in the basic scheduling procedure.

## Slide 4: Burgess Procedure
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H | 2 | 2 | 2 | 2 | 2 |  |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 5 | 5 | 5 | 5 | 6 | 4 | 7 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 25 | 25 | 25 | 25 | 36 | 16 | 49 | 25 | 25

## Slide 5: Iterate Activity “H”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H | 2 | 2 | 2 | 2 | 2 |  |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 5 | 5 | 5 | 5 | 6 | 4 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 25 | 25 | 25 | 25 | 36 | 16 | 25 | 25 | 25
R2 = 743

## Slide 6: Delay Activity “H” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 747

## Slide 7: Delay Activity “H” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  | 2 | 2 | 2 | 2 | 2 |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 5 | 5 | 6 | 6 | 7 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 9 | 25 | 25 | 36 | 36 | 49 | 25 | 25
R2 = 755

## Slide 8: Delay Activity “H” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  | 2 | 2 | 2 | 2 | 2 | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 3 | 5 | 6 | 6 | 7 | 7 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 9 | 9 | 25 | 36 | 36 | 49 | 49 | 25
R2 = 763

## Slide 9: Delay Activity “H” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 3 | 3 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 9 | 9 | 9 | 36 | 36 | 49 | 49 | 49
R2 = 798

## Slide 10: Minimum R2 = Delay activity “H” 1 period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 747

## Slide 11: Iterate Activity “G”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 747

## Slide 12: Delay Activity “G” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 9 | 9 | 6 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 81 | 81 | 36 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 13: Stop Delay for Dependency
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 9 | 9 | 6 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 81 | 81 | 36 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 14: Iterate Activity “F”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 9 | 9 | 6 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 81 | 81 | 36 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 15: Delay Activity “F” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 9 | 9 | 7 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 81 | 81 | 49 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 731

## Slide 16: Delay Activity “F” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 8 | 9 | 7 | 7 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 64 | 81 | 49 | 49 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 727

## Slide 17: Delay Activity “F” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 8 | 8 | 7 | 7 | 6 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 64 | 64 | 49 | 49 | 36 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 721

## Slide 18: Delay Activity “F” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 8 | 8 | 6 | 7 | 6 | 6 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 64 | 64 | 36 | 49 | 36 | 36 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 719

## Slide 19: Delay Activity “F” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 64 | 64 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 717

## Slide 20: Minimum R2 = Delay activity “F” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 64 | 64 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 717

## Slide 21: Iterate Activity “E”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 5 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 25 | 64 | 64 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 717

## Slide 22: Delay Activity “E” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 64 | 64 | 64 | 36 | 36 | 36 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 23: Delay Activity “E” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 64 | 64 | 64 | 36 | 36 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 24: Delay Activity “E” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 25: Delay Activity “E” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 26: Delay Activity “E” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 27: Minimum R2 = Delay activity “E” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 28: Iterate Activity “D”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 29: Delay Activity “D” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 713

## Slide 30: Delay Activity “D” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 10 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 100 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 721

## Slide 31: Delay Activity “D” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  |  |  | 4 | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 3 | 10 | 10 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 25 | 9 | 100 | 100 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 745

## Slide 32: Delay Activity “D” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  |  |  |  | 4 | 4 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 3 | 6 | 10 | 10 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 25 | 9 | 36 | 100 | 100 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 745

## Slide 33: Delay Activity “D” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  |  |  |  |  | 4 | 4 |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 3 | 6 | 6 | 10 | 10 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 25 | 9 | 36 | 36 | 100 | 100 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 745

## Slide 34: Minimum R2 = Delay activity “D” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 713

## Slide 35: After First Rescheduling Cycle
Delay activity “H” one period   R2 = 747
Delay activity “G” one period   R2 = 729
Delay activity “F” five periods   R2 = 717
Delay activity “E” five periods   R2 = 729
Delay activity “D” one periods   R2 = 713

## Slide 36: Iterate Activity “H”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 713

## Slide 37: Delay Activity “H” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  | 2 | 2 | 2 | 2 | 2 |  | 
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 8 | 8 | 6 | 6 | 7 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 36 | 64 | 64 | 36 | 36 | 49 | 25 | 25
R2 = 709

## Slide 38: Delay Activity “H” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  | 2 | 2 | 2 | 2 | 2 | 
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 6 | 6 | 7 | 7 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 36 | 36 | 64 | 36 | 36 | 49 | 49 | 25
R2 = 709

## Slide 39: Delay Activity “H” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49
R2 = 709

## Slide 40: Schedule Late possible Activity
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49
R2 = 709

## Slide 41: Iterate Activity “G”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49
R2 = 709

## Slide 42: Delay Activity “G” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 3 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 9 | 36 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 727

## Slide 43: Delay Activity “G” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 3 | 3 | 6 | 6 | 9 | 9 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 9 | 9 | 36 | 36 | 81 | 81 | 36 | 36 | 36 | 49 | 49 | 49
R2 = 745

## Slide 44: Delay Activity “G” 3 period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  |  |  | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 3 | 3 | 3 | 6 | 9 | 9 | 9 | 6 | 6 | 7 | 7 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 9 | 9 | 9 | 36 | 81 | 81 | 81 | 36 | 36 | 49 | 49 | 25
R2 = 763

## Slide 45: Minimum R2 = Delay activity “G” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 3 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 9 | 36 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 727

## Slide 46: Iterate Activity “D”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 3 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 9 | 36 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 727

## Slide 47: Delay Activity “D” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 49 | 36 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 711

## Slide 48: Delay Activity “D” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  |  |  | 4 | 4 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 3 | 7 | 100 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 25 | 9 | 49 | 100 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 735

## Slide 49: Delay Activity “D” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  |  |  |  | 4 | 4 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 100 | 10 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 25 | 9 | 9 | 100 | 100 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 759

## Slide 50: Delay Activity “D” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  |  |  |  |  | 4 | 4 |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 6 | 10 | 10 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 25 | 9 | 9 | 36 | 100 | 100 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 759

## Slide 51: Minimum R2 = Delay activity “D” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 49 | 36 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 49 | 49 | 46
R2 = 711

## Slide 52: After Second Rescheduling Cycle
Delay activity “H” three period   R2 = 709
Delay activity “G” one period   R2 = 727
Delay activity “D” one periods   R2 = 711

## Slide 53: Final Activity Scheduling
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  |  |  |  | 2 | 2 | 2 | 2 | 2
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49
R2 = 709

## Slide 54: Estimated Method
Step 1: Draw the network in a time scaled diagram using the early start schedule method.
Step 2: Perform resource loading for the activities and calculate the total number of resources at each period.
Step 3: Reschedule non-critical activities to reduce peaks and to smooth resource usage in the resource loading chart in order to minimize SUM Yi2, where Yi is the number of resource usage in the resource loading chart.
Step 4: Continue Step 3 until you reach the schedule of having minimum value of SUM Yi2.

## Slide 55: Resource Leveling
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
I |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
J |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
K |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  |  | H | 2 | 2 | 2 | 2 | 2 |  |  |  | 
D |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
Daily R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 5 | 5 | 5 | 5 | 6 | 4 | 5 | 5 | 5
R | 5 | 10 | 15 | 24 | 33 | 42 | 51 | 60 | 66 | 71 | 76 | 81 | 86 | 92 | 96 | 101 | 106 | 111
R2 | 25 | 50 | 75 | 156 | 237 | 318 | 399 | 480 | 516 | 541 | 566 | 591 | 616 | 652 | 668 | 693 | 718 | 743
10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 |  |  |  | Resource Loading Diagram = Resource Histogram |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 56: Resource Leveling
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 2 | 2 | 2 | 2
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 6 | 6 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 36 | 36 | 9 | 36 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49
Delay activity “H” 4 periods & Delay activity “G” 4 period   R2 = 717

## Slide 57: Resource Leveling
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 2 | 2 | 2 | 2
 |  |  |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 49 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49
Delay activity “H” 4 periods, Delay activity “G” 4 periods, Delay activity “E” 2 periods, Delay activity “F” 2 periods, and Delay activity “D” 2 periods   R2 = 703

## Slide 58: Resource Leveling
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | G | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | H | 2 | 2 | 2 | 2 | 2
 |  |  |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 5 | 5 | 8 | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 7
R2 | 25 | 50 | 75 | 100 | 125 | 174 | 223 | 248 | 273 | 337 | 386 | 435 | 484 | 520 | 556 | 605 | 654 | 703
Delay activity “H” 4 periods, Delay activity “G” 4 periods, Delay activity “F” 5 periods, Delay activity “E” 2 periods, and Delay activity “D” 2 periods   R2 = 703

## Slide 59: Iterate Activity “E”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 9 | 9 | 6 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 81 | 81 | 36 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 60: Delay Activity “E” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 9 | 9 | 8 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 81 | 81 | 64 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 737

## Slide 61: Delay Activity “E” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 7 | 8 | 8 | 8 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 49 | 64 | 64 | 64 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 733

## Slide 62: Delay Activity “E” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 7 | 7 | 8 | 8 | 7 | 5 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 49 | 49 | 64 | 64 | 49 | 25 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 742

## Slide 63: Delay Activity “E” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 7 | 7 | 6 | 8 | 7 | 7 | 5 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 49 | 49 | 36 | 64 | 49 | 49 | 25 | 36 | 36 | 25 | 25 | 25
R2 = 738

## Slide 64: Delay Activity “E” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 49 | 49 | 36 | 36 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 734

## Slide 65: Minimum R2 = Delay activity “E” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 49 | 49 | 36 | 36 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 734

## Slide 66: Iterate Activity “F”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 4 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 16 | 49 | 49 | 36 | 36 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 734

## Slide 67: Delay Activity “F” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 7 | 7 | 7 | 6 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 49 | 49 | 49 | 36 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 740

## Slide 68: Delay Activity “F” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 49 | 49 | 49 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 740

## Slide 69: Delay Activity “F” 3 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 7 | 7 | 8 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 49 | 49 | 64 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 742

## Slide 70: Delay Activity “F” 4 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 6 | 7 | 8 | 8 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 36 | 49 | 64 | 64 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 744

## Slide 71: Delay Activity “F” 5 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 36 | 36 | 36 | 64 | 64 | 64 | 36 | 36 | 25 | 25 | 25
R2 = 729

## Slide 73: Minimum R2 = Delay activity “F” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 49 | 49 | 49 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 740

## Slide 74: Iterate Activity “D”
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 3 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 81 | 81 | 9 | 36 | 49 | 49 | 49 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 740

## Slide 75: Delay Activity “D” 1 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 9 | 7 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 81 | 49 | 36 | 49 | 49 | 49 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 724

## Slide 76: Delay Activity “D” 2 Period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | 3 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | C | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | I | 3 | 3 | 3 | 3 |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  | J | 4 | 4 |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | K | 5 | 5 | 5
B | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | G |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | H |  | 2 | 2 | 2 | 2 | 2 |  |  | 
 |  |  | D |  |  | 4 | 4 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | E |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
 |  |  |  |  | F |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 100 | 49 | 49 | 49 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25
R2 = 732