## Slide 1: Project Management Probabilistic approach
Operations Management
by
R. Dan Reid & Nada R. Sanders
3th Edition © Wiley 2010

## Slide 2: Network Planning Techniques
Program Evaluation & Review Technique (PERT):
  Developed to manage the Polaris missile project
  Many tasks pushed the boundaries of science & engineering (tasks’ duration = probabilistic)
Critical Path Method (CPM):
  Developed to coordinate maintenance projects in the chemical industry
  A complex undertaking, but individual tasks are routine (tasks’ duration = deterministic)

## Slide 3: Both PERT and CPM
Graphically display the precedence relationships & sequence of activities
Estimate the project’s duration
Identify critical activities that cannot be delayed without delaying the project
Estimate the amount of slack associated with non-critical activities

## Slide 4: Network Diagrams
Activity-on-Node (AON):
  Uses nodes to represent the activity
  Uses arrows to represent precedence relationships

## Slide 5: Step 1-Define the Project: Cables By Us is bringing a new product on line to be manufactured in their current facility in some existing space. The owners have identified 11 activities and their precedence relationships. Develop an AON for the project.

## Slide 6: Step 2- Diagram the Network for Cables By Us

## Slide 7: Step 3 (a)- Add Deterministic Time Estimates and Connected Paths

## Slide 8: Step 3 (a) (Continued): Calculate the Path Completion Times
The longest path (ABDEGIJK) limits the project’s duration (project cannot finish in less time than its longest path)
ABDEGIJK is the project’s critical path

## Slide 9
Program Evaluation and Review Technique

## Slide 10: Estimation of Task Times
In CPM, we assume that the task durations are known with certainty.
This may not be realistic in many project settings.
  How long does it take to design a switch?
PERT tries to account for the uncertainty in task durations.
Key question: What is the probability of completing project by given deadline?

## Slide 11: CPM vs. PERT
  CPM (critical path method)
  PERT (program evaluation and review technique)
Both approaches work on a project network, which graphically portrays the activities of the project and their relationships.
CPM assumes that activity times are deterministic, while PERT views the time to complete a task as a random variable.

## Slide 12: Estimation of the duration of project activities
(1) The deterministic approach (CPM), which ignores uncertainty thus results in a point estimate (e.g. The duration of task 1 = 23 hours, etc.)
(2) The stochastic approach (PERT), which considers the uncertain nature of project activities by estimating the expected duration of each activity and its corresponding variance.
  To analyse the past data to construct the probabilistic distribution of a task.

## Slide 13: Estimation of the activity duration
Example: An activity was performed 40 times in the past, requiring a time between 10 to 70 hours. The figure below shows the frequency distribution.

## Slide 14: Estimation of the activity duration
The probability distribution of the activity is approximated by a probability frequency distribution.

## Slide 15: Estimation of the activity duration
In project scheduling, we usually use a beta distribution to represent the time needed for each activity.

## Slide 16: Estimation of the activity duration
Three key values we use in the time estimate for each activity:
  a = optimistic time, which means that there is little chance that the activity can be completed before this time;
  m = most likely time, which will be required if the execution is normal;
  b = pessimistic time, which means that there is little chance that the activity will take longer.

## Slide 17: Estimation of Mean and SD
The expected or mean time is given by:
      D= (a+4m+b)/6
The variance is:
V = (b-a) 2/36
The standard deviation is (b - a)/6
For our example (Figure 7-3), we have a=10, b=70, m=35.
Therefore D=36.6, and V2 =100.

## Slide 18: Estimation of Mean and SD
Expected task time:
Standard deviation:
m
b
Beta-distribution
a

## Slide 19: The PERT Approach
The PERT (Program evaluation and review technique) approach addresses situations where uncertainties must be considered.

## Slide 20: The PERT Approach (cont’d)
Now assume that the activity times are independent random variables.
Further, assume that there are n activities in the project, k of which are critical. Denote the activity times of the critical activities by the random variables di with mean E(di) and variances V(di), for i=1,2, …, k.
Then, the total project time (the total length of the critical path) is the random variable:
X= d1 + d2 +,…, +dk

## Slide 21: The PERT Approach (cont’d)
The mean project length, E(X), and its variance, V(X):
E(X)= E(d1)+E(d2)+,…, +E(dk)
V(X)= V(d1)+V(d2)+,…, +V(dk)
Assumption:
  Activity times are independent random variables.
  The project duration (=sum of times of activity on a critical path) is normally distributed.
    Based on the Central Limit Theorem, which states that the distribution of the sum of independent random variables is approximately normal when the number of terms in the sum if sufficiently large.

## Slide 23: Example: Shopping Mall Renovation
Activity IP a m b
A: Prepare initial design - 1 3 5
B: Identify new potential clients - 4 5 12
C: Develop prospectus for tenants A 2 3 10
D: Prepare final design A 1 8 9
E: Obtain planning permission D 1 2 3
F: Obtain finance from bank E 1 3 5
G: Select contractor D 2 4 6
H: Construction G, F 10 17 18
I: Finalize tenant contracts B, C, E 6 13 14
J: Tenants move in I, H 1 2 3

## Slide 24: Example: Issues to Address
Schedule the project.
2. What is the probability of completing the project in 36 weeks?

## Slide 25: Expected Activity Time and SD
Act a m b t 2
A 1 3 5 3 0.44
B 4 5 12 6 1.78
C 2 3 10 4 1.78
D 1 8 9 7 1.78
E 1 2 3 2 0.11
F 1 3 5 3 0.44
G 2 4 6 4 0.44
H 10 17 18 16 1.78
I 6 13 14 12 1.78
J 1 2 3 2 0.11

## Slide 26: CPM with Expected Activity Times
1
A,3
D,7
E,2
H,16
J,2
I,12
End
B,6
C,4
F,3
G,4

## Slide 27: Critical Path and Expected Time
Critical path: A-D-E-F-H-J.
Expected Completion time: 33 weeks
What is the probability to complete the project within 36 weeks?
  -- Use the critical path to assess the probability

## Slide 28: Probability Assessment
Expected project completion time:
Sum of the expected activity times
along the critical path.
 = 3+7+2+3+16+2 = 33
Variance of project-completion time
Sum of the variances along
the critical path.
2 = 0.44+1.78+0.11+0.44+1.78+0.11= 4.66
 = 2.15
Used to obtain
probability of project
completion

## Slide 29: Assessment by Normal Distribution
Assume X ~ N(33, 2.152)
P(X  36) = ?

= 33

= 2.15
36
X
Normal Distribution
z
T

=
-
=
-
=

36
33
2.15
1.4
.

z
= 0

z
= 1
Z
1.4
Standardized Normal Distribution
P(Z  1.4) = ?

## Slide 30: Obtain the Probability
z=0
z=1
z
1.4
Z
.00
.01
.02
0.0
.5000
.5040
.5080
:
:
:
:
1.4
.9192
.9207
.9222
1.5
.9332
.9345
.9357
Standardized Normal Probability Table (Portion)
P( 0 < Z < z )
.9192
P(Z<1.4) = 0.9192

## Slide 31: Completion Time with a Given Prob.
Using PERT, it is also possible to estimate the completion time for a desired completion probability.
For example, for a 95% probability the corresponding Z value is Z0.95 = 1.64. Solving for the time T for which the probability to complete the project is 95%, we get
Z0.95 = (T – 33)/2.15 = 1.64
T = 33 + (2.15)(1.64) = 36.5

## Slide 32: A Shortcoming of Standard PERT
The standard PERT method ignores all activities not on the critical path.
What is the probability to complete the project within 17 weeks?

## Slide 33: A Modification
Identify each sequence of activities leading from the start to the end, and then calculate separately the probability for each path to complete by a given date.
The above can be done by assuming that the central limit theorem holds for each sequence and then applying normal distribution theory to calculate the individual sequence (path) probabilities.
Assume, if necessary, that the paths are statistically independent (i.e. the time to traverse each path in the network is independent of what happens on the other paths).
Although this additional assumption is rarely true in practice, empirical evidence suggests that good results can be obtained.

## Slide 34: Modified Probability of Completion
Once the calculations on all paths (at least those that we are concerned with) are performed, the probability of completing the whole project can be calculated.
Assume there are n paths, with completion times X1, X2, …, Xn. Then, the probability of completing the project is
P(X  T) = P(X1  T) P(X2  T) … P(Xn  T)

## Slide 35: Example: Modified Calculations
If no uncertainty exists, then the critical path is (A-B) and exactly 17 weeks are required to finish the project.
If the durations of the four activities are normally distributed (the means and variances are as shown in the figure above), then the durations of the two paths are normally distributed as follows:
length (A-B) = X1 ~ N(17, 3.61)
length (C-D) = X2 ~ N(16, 3.35)

## Slide 36: The Probability Density Functions

## Slide 37: Project Completion Probabilities
The project can be completed in 17 weeks only if both (A-B) and (C-D) are completed within that time. The probabilities for the two paths to be completed in that time are given below:
17-17
P(X1  17) = P(Z  ----------- ) = P(Z  0)=0.5
3.61
17-16
P(X2  17) = P(Z  ----------- ) = P(Z  0.299)=0.62
3.35
Thus, the probability of completing the project within 17 weeks is
P(X  17) = P(X1  17) P(X2  17) = (0.5)(0.62)=0.31 = 31 %.

## Slide 38: Revisiting Cables By Us Using Probabilistic Time Estimates

## Slide 39: Using Beta Probability Distribution to Calculate Expected Time Durations
A typical beta distribution is shown below, note that it has definite end points
The expected time for finishing each activity is a weighted average

## Slide 40: Calculating Expected Task Times

## Slide 41: Network Diagram with Expected Activity Times

## Slide 42: Estimated Path Durations through the Network
ABDEGIJK is the expected critical path & the project has an expected duration of 44.83 weeks

## Slide 43: Estimating the Probability of Completion Dates
Using probabilistic time estimates offers the advantage of predicting the probability of project completion dates
We have already calculated the expected time for each activity by making three time estimates
Now we need to calculate the variance for each activity
The variance of the beta probability distribution is:
  where p=pessimistic activity time estimate
o=optimistic activity time estimate

## Slide 44: Project Activity Variances
Activity | Optimistic | Most Likely | Pessimistic | Variance
A | 2 | 4 | 6 | 0.44
B | 3 | 7 | 10 | 1.36
C | 2 | 3 | 5 | 0.25
D | 4 | 7 | 9 | 0.69
E | 12 | 16 | 20 | 1.78
F | 2 | 5 | 8 | 1.00
G | 2 | 2 | 2 | 0.00
H | 2 | 3 | 4 | 0.11
I | 2 | 3 | 5 | 0.25
J | 2 | 4 | 6 | 0.44
K | 2 | 2 | 2 | 0.00

## Slide 45: Critical Activity Variances
Activity | Optimistic | Most Likely | Pessimistic | Variance
A | 2 | 4 | 6 | 0.44
B | 3 | 7 | 10 | 1.36
C | 2 | 3 | 5 | 0.25
D | 4 | 7 | 9 | 0.69
E | 12 | 16 | 20 | 1.78
F | 2 | 5 | 8 | 1.00
G | 2 | 2 | 2 | 0.00
H | 2 | 3 | 4 | 0.11
I | 2 | 3 | 5 | 0.25
J | 2 | 4 | 6 | 0.44
K | 2 | 2 | 2 | 0.00
Critical activities highlighted
Sum over critical = 4.96

## Slide 46: Calculating the Probability of Completing the Project in Less Than a Specified Time
When you know:
  The expected completion time EFP
  Its variance Path2
You can calculate the probability of completing the project in “DT” weeks with the following formula:
Where DT = the specified completion date
EFPath = the expected completion time of the path

## Slide 47: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 1: What is the probability of completing project (along critical path) within 48 weeks?

## Slide 48: Probability of completion by DT
Z92 = 1.42
z
0
Project not finished
by the given date
Tail Area = .0778
Area = .4222
Area left of y-axis = .50
Probability = .4222+ .5000 =.9222 or 92.22%

## Slide 49: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 2: By how many weeks are we 95% sure of completing project (along critical path)?

## Slide 50: Probability Question 2
Z95 = 1.645
z
0
Tail Area = .05
Area = .45
Area left of y-axis = .50
DT = 48.5 weeks

## Slide 51: Reducing Project Completion Time
Project completion times may need to be shortened because
  Different deadlines
  Penalty clauses
  Need to put resources on a new project
  Promised completion dates
Reduced project completion time is “crashing”

## Slide 52: Reducing Project Completion Time - continued
Crashing a project needs to balance
  Shorten a project duration
  Cost to shorten the project duration
Crashing a project requires you to know
  Crash time of each activity
  Crash cost of each activity

## Slide 53: The Critical Chain Approach
The Critical Chain Approach focuses on the project due date rather than on individual activities and the following realities:
  Project time estimates are uncertain so we add safety time
  Multi-levels of organization may add additional time to be “safe”
  Individual activity buffers may be wasted on lower-priority activities
  A better approach is to place the project safety buffer at the end
Original critical path |  |  |  |  |  |  |  |  | 
Activity A |  | Activity B |  | Activity C |  |  | Activity D |  | Activity E
Critical path with project buffer |  |  |  |  |  |  |  |  | 
Activity A | Activity B |  | Activity C |  | Activity D | Activity E |  | Project Buffer | 

## Slide 54: Adding Feeder Buffers to Critical Chains
The theory of constraints, the basis for critical chains, focuses on keeping bottlenecks busy.
Time buffers can be put between bottlenecks in the critical path
These feeder buffers protect the critical path from delays in non-critical paths

## Slide 55: Approaches to Project Implementation
Pure Project
Functional Project
Matrix Project

## Slide 56: Advantages
A PURE PROJECT is where a self-contained team works full-time on the project
The project manager has full authority over the project
Team members report to one boss
Shortened communication lines
Team pride, motivation, and commitment are high
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 8

## Slide 57
Duplication of resources
Organizational goals and policies are ignored
Lack of technology transfer
Team members have no functional area "home"
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Pure Project: Disadvantages
Notes: 8

## Slide 58: Functional Project
President
Research and
Development
Engineering
Manufacturing
Project
A
Project
B
Project
C
Project
D
Project
E
Project
F
Project
G
Project
H
Project
I
housed within a functional division
Example, Project “B” is in the functional area of Research and Development.
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 9

## Slide 59: Functional Project: Advantages
A team member can work on several projects
Technical expertise is maintained within the functional area
The functional area is a “home” after the project is completed
Critical mass of specialized knowledge
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 10

## Slide 60: Functional Project: Disadvantages
Aspects of the project that are not directly related to the functional area get short-changed
Motivation of team members is often weak
Needs of the client are secondary and are responded to slowly
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 11

## Slide 61: Matrix Project: combines features of pure and functional
President
Research and
Development
Engineering
Manufacturing
Marketing
Manager
Project A
Manager
Project B
Manager
Project C
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 12

## Slide 62: Matrix Project: Advantages
Enhanced communications between functional areas
Pinpointed responsibility
Duplication of resources is minimized
Functional “home” for team members
Policies of the parent organization are followed
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 13

## Slide 63: Matrix Project: Disadvantages
Too many bosses
Depends on project manager’s negotiating skills
Potential for sub-optimization
Source: Chase, Jacobs & Aquilano, Operations Management 11/e
Notes: 14

## Slide 64: Additional Example
Note: activity “0” is a formality.
Source: Chase, Jacobs & Aquilano, Operations Management 11/e

## Slide 65: Additional Example
Note: activity “0” is a formality.
Source: Chase, Jacobs & Aquilano, Operations Management 11/e

## Slide 66: Additional Example, continued
A
B
0
C
D
E
F
G
H
3
2
2
3
5
4
3.83
3.83
paths
0ACFH
0ADFH
0ADGH
0BEGH

## Slide 67: Additional Example, continued
A
B
0
C
D
E
F
G
H
3
2
2
3
5
4
3.83
3.83
Critical Path: 0-B-E-G-H
Length = 14.67

## Slide 68
A
B
0
C
D
E
F
G
H
.83
0
1.83
0
.83
0
0
.83
Add variances along path
to get path variance
0.11
1.78
0.69
0.25
total=2.83
Additional Example, continued.

## Slide 69: Probabilistic Analysis
14.67
16
Project completion times assumed normally distributed with mean 14.67 and variance 2.83
Z-score
From table look-up, P(DT16) = .7549
Find the probability of completing the project within 16 days.
Additional Example, continued.

## Slide 70: Probabilistic Analysis
Project completion times assumed normally distributed with mean 14.67 and variance 2.83
Z95 = 1.645, thus
Solving for X=17.44 days
Find the 95-th percentile of project completion.
14.67
17.44
Additional Example, continued.

## Slide 71: Example 2, #13-14 Ch 16:

## Slide 72: Example 2, #13-14 Ch 16:

## Slide 73: Example 2, #13-14 Ch 16:
A(10)
B(10)
D(8)
F(7.17)
C(5)
E(7.33)
G(8)
H(3)

## Slide 74: Example 2, #13-14 Ch 16: PATH 1
A(10)
B(10)
D(8)
F(7.17)
H(3)
Length = 38.17

## Slide 75: Example 2, #13-14 Ch 16: PATH 2
A(10)
C(5)
E(7.33)
G(8)
H(3)
Length = 33.33

## Slide 76: Example 2, #13-14 Ch 16: PATH 3
A(10)
B(10)
D(8)
G(8)
H(3)
Length = 39

## Slide 77: Example 2, #13-14 Ch 16: PATH 4
A(10)
F(7.17)
C(5)
E(7.33)
H(3)
Length = 32.5

## Slide 78: Example 2, #13-14 Ch 16: CRITICAL PATH
A(10)
B(10)
D(8)
G(8)
H(3)
Length = 39
Path variance = 6.67

## Slide 79: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 1: What is the probability of completing project (along critical path) within 36 weeks?

## Slide 80: Probability of completion by DT
Z = -1.16
z
0
Project finished
by the given date
Tail Area = .1230
Area = .3770
Area left of y-axis = .50
Probability =
.5000 - 3770
=.1230 or 12.3%

## Slide 81: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 2: What is the probability of completing project (along critical path) within 40 weeks?
Probability = .6517 = 65.17%
Question 3: By how many weeks are we 99% sure of completing project (along critical path)?
DT = 45.02 weeks

## Slide 82: Example 3, #4-8 Ch 16:

## Slide 83: Example 3, #4-#8 Ch 16:
A(6)
B(5)
D(7.67)
F(4)
C(7.33)
E(10.17)
G(5.83)
H(6.5)
I(8)
J(3)

## Slide 84: Example 3, #4-#8 Ch 16:
A(6)
B(5)
D(7.67)
F(4)
C(7.33)
E(10.17)
G(5.83)
H(6.5)
I(8)
J(3)
length =32.17

## Slide 85: Example 3, #4-#8 Ch 16:
A(6)
B(5)
D(7.67)
F(4)
C(7.33)
E(10.17)
G(5.83)
H(6.5)
I(8)
J(3)
length = 35.50

## Slide 86: Example 3, #4-#8 Ch 16:
A(6)
B(5)
D(7.67)
F(4)
C(7.33)
E(10.17)
G(5.83)
H(6.5)
I(8)
J(3)
length =37

## Slide 87: Example 3, #4-#8 Ch 16:
A(6)
B(5)
D(7.67)
F(4)
C(7.33)
E(10.17)
G(5.83)
H(6.5)
I(8)
J(3)
length = 40.33 CRITICAL PATH

## Slide 88: Example 3, #4-#8 Ch 16:
A(6)
B(5)
D(7.67)
F(4)
C(7.33)
E(10.17)
G(5.83)
H(6.5)
I(8)
J(3)
Path variance =1+1.78+3.36+0.69+1+0 = 7.83

## Slide 89: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 1: What is the probability of completing project (along critical path) within 38 weeks?

## Slide 90: Probability of completion by DT=38
Z = -0.83
z
0
Project finished
by the given date
Tail Area = .2033
Area = .2967
Area left of y-axis = .50
Probability =
.5000 - 2967
=.2033 or 20.33%

## Slide 91: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 2: What is the probability of completing project (along critical path) within 42 weeks?
Probability = .2257+.5000 = .7257 = 72.57%

## Slide 92: Apply z formula to critical path
Use Standard Normal Table (Appendix B) to answer probabilistic questions, such as
Question 3: By how many weeks are we 99% sure of completing project (along critical path)?
DT = 46.85 weeks