## Slide 1: Early Activity Time
The "Early Start" (ES) or "Earliest Start" of an activity is the earliest time that the activity can possibly start allowing for the time required to complete the preceding activities.
The "Early Finish" (EF) or "Earliest Finish" of an activity is the earliest possible time that it can be completed and is determined by adding that activity's duration to its early start time.

## Slide 2: Late Activity Time
The "late finish" (LF) or "Latest Finish" of an activity is the very latest that it can finish and allow the entire project to be completed by a designated time or date.
The “late start” (LS) or "Latest Start" of an activity is the latest possible time that it can be started if the project target completion date is to be met and is obtained by subtracting the activity's duration from its latest finish time.

## Slide 3: Activity
Activity | Depends on | Relation | Duration
A | - | - | 5
B | A | FS 1 | 5
C | A | SS 2 | 6
D | B, C | FS, FS -1 | 2
E | D | FF 2 | 3
F | D | SF (1,2) | 1
G | E, F | ZZ (2,6), FS 2 | 4

## Slide 4: Activity on Node Network
A |  | 
 | 5 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 5: Activity on Node Network
A |  | 
 | 5 | 
B |  | 
 | 5 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 6: Activity on Node Network
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 7: Activity on Node Network
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
D |  | 
 | 2 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 8: Activity on Node Network
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 9: Activity on Node Network
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 10: Activity on Node Network
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Activity | Depends on | Duration
A | - | 5
B | A | 5
C | A | 6
D | B, C | 2
E | D | 3
F | D | 1
G | E, F | 4

## Slide 11: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 

## Slide 12: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
C |  | 
 | 6 | 
5 |  | 10
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 

## Slide 13: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
5 |  | 11
C |  | 
 | 6 | 
5 |  | 10
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 

## Slide 14: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
5 |  | 11
C |  | 
 | 6 | 
5 |  | 10
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Max (10,11)

## Slide 15: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
5 |  | 11
C |  | 
 | 6 | 
5 |  | 10
B |  | 
 | 5 | 
F |  | 
 | 1 | 
13 |  | 16
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
G |  | 
 | 4 | 

## Slide 16: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
5 |  | 11
C |  | 
 | 6 | 
5 |  | 10
B |  | 
 | 5 | 
13 |  | 14
F |  | 
 | 1 | 
13 |  | 16
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
G |  | 

## Slide 17: Forward Pass
0 |  | 5
A |  | 
 | 5 | 
5 |  | 11
C |  | 
 | 6 | 
5 |  | 10
B |  | 
 | 5 | 
13 |  | 14
F |  | 
 | 1 | 
13 |  | 16
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
16 |  | 20
G |  | 
 | 4 | 
Max(16,14)

## Slide 18: Backward Pass
0 |  | 5
A |  | 
5 |  | 11
C |  | 
5 |  | 10
B |  | 
13 |  | 14
F |  | 
13 |  | 16
E |  | 
11 |  | 13
D |  | 
16 |  | 20
G |  | 
16 | 4 | 20

## Slide 19: Backward Pass
0 |  | 5
A |  | 
5 |  | 11
C |  | 
5 |  | 10
B |  | 
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
11 |  | 13
D |  | 
16 |  | 20
G |  | 
16 | 4 | 20

## Slide 20: Backward Pass
0 |  | 5
A |  | 
5 |  | 11
C |  | 
5 |  | 10
B |  | 
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
13 | 3 | 16
11 |  | 13
D |  | 
16 |  | 20
G |  | 
16 | 4 | 20

## Slide 21: Backward Pass
0 |  | 5
A |  | 
5 |  | 11
C |  | 
5 |  | 10
B |  | 
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
13 | 3 | 16
11 |  | 13
D |  | 
11 | 2 | 13
16 |  | 20
G |  | 
16 | 4 | 20
Min(13,15)

## Slide 22: Backward Pass
0 |  | 5
A |  | 
5 |  | 11
C |  | 
5 | 6 | 11
5 |  | 10
B |  | 
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
13 | 3 | 16
11 |  | 13
D |  | 
11 | 2 | 13
16 |  | 20
G |  | 
16 | 4 | 20

## Slide 23: Backward Pass
0 |  | 5
A |  | 
5 |  | 11
C |  | 
5 | 6 | 11
5 |  | 10
B |  | 
6 | 5 | 11
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
13 | 3 | 16
11 |  | 13
D |  | 
11 | 2 | 13
16 |  | 20
G |  | 
16 | 4 | 20

## Slide 24: Backward Pass
0 |  | 5
A |  | 
0 | 5 | 5
5 |  | 11
C |  | 
5 | 6 | 11
5 |  | 10
B |  | 
6 | 5 | 11
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
13 | 3 | 16
11 |  | 13
D |  | 
11 | 2 | 13
16 |  | 20
G |  | 
16 | 4 | 20
Min(6,5)

## Slide 25: Critical Path
0 |  | 5
A |  | 
0 | 5 | 5
5 |  | 11
C |  | 
5 | 6 | 11
5 |  | 10
B |  | 
6 | 5 | 11
13 |  | 14
F |  | 
15 | 1 | 16
13 |  | 16
E |  | 
13 | 3 | 16
11 |  | 13
D |  | 
11 | 2 | 13
16 |  | 20
G |  | 
16 | 4 | 20

## Slide 26
A |  | 
 | 5 | 
C |  | 
 | 6 | 
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Precedence Diagram with Relation
Activity | Depends on | Relation
A | - | -
B | A | FS 1
C | A | SS 2
D | B, C | FS, FS -1
E | D | FF 2
F | D | SF (1,2)
G | E, F | ZZ(2,6), FS2
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2

## Slide 27: Precedence Diagram Computation
Forward Pass Computations |  |  | 
[1] ESj = | Max. all i |  | Initial Time EFi + FSij ESi + SSij EFi + FFij – Dj ESi + SFij - Dj
[2] EFj = ESj + Dj |  |  | 

## Slide 28
0 |  | 5
A |  | 
 | 5 | 
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Precedence Diagram Forward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
ESB = EFA + FSAB
EFB = DB + ESB

## Slide 29
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Precedence Diagram Forward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
ESC = ESA + SSAC
EFC = DC + ESC

## Slide 30
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
F |  | 
 | 1 | 
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Precedence Diagram Forward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
ESD = MAX(EFB + FSBD , EFC + FSCD)
EFD = DD + ESD

## Slide 31
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
F |  | 
 | 1 | 
12 |  | 15
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Precedence Diagram Forward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
ESE = EFD + FFDE - DE
EFE = DE + ESE

## Slide 32
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
13 |  | 14
F |  | 
 | 1 | 
12 |  | 15
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
G |  | 
 | 4 | 
Precedence Diagram Forward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
ESF = ESD + SFDF - DF
EFF = DF + ESF

## Slide 33
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
13 |  | 14
F |  | 
 | 1 | 
12 |  | 15
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
17 |  | 21
G |  | 
 | 4 | 
Precedence Diagram Forward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
ESG = MAX(ESE + SSEG , EFE+ FFEG- DG , EFF + FSFG)
EFG = DG + ESG

## Slide 34
Backward Pass Computations |  |  | 
[3] LFi = | Min. all j |  | Terminal Time LSj - FSij LFj - FFij LSj - SSij + Di LFj - SFij + Di
[4] LSi = LFi  Di |  |  | 
Precedence Diagram Computation

## Slide 35
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
 | 3 | 
11 |  | 13
D |  | 
 | 2 | 
17 |  | 21
G |  | 
17 | 4 | 21
Precedence Diagram Backward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
LFF = LSG - FSFG
LSF = LFF - DF

## Slide 36
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
12 | 3 | 15
11 |  | 13
D |  | 
 | 2 | 
17 |  | 21
G |  | 
17 | 4 | 21
Precedence Diagram Backward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
LFE = MIN(LSG - SSEG + DE , LFG - FFEG )
LSE = LFE - DE

## Slide 37
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
 | 6 | 
6 |  | 11
B |  | 
 | 5 | 
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
12 | 3 | 15
11 |  | 13
D |  | 
11 | 2 | 13
17 |  | 21
G |  | 
17 | 4 | 21
Precedence Diagram Backward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
LFD = MIN(LFF - SFDF + DD , LFE - FFFE )
LSD = LFD - DD

## Slide 38
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
6 | 6 | 12
6 |  | 11
B |  | 
 | 5 | 
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
12 | 3 | 15
11 |  | 13
D |  | 
11 | 2 | 13
17 |  | 21
G |  | 
17 | 4 | 21
Precedence Diagram Backward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
LFC = LSD - FSCD
LSC = LFC - DC

## Slide 39
0 |  | 5
A |  | 
 | 5 | 
2 |  | 8
C |  | 
6 | 6 | 12
6 |  | 11
B |  | 
6 | 5 | 11
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
12 | 3 | 15
11 |  | 13
D |  | 
11 | 2 | 13
17 |  | 21
G |  | 
17 | 4 | 21
Precedence Diagram Backward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
LFB = LSD - FSBD
LSB = LFB - DB

## Slide 40
0 |  | 5
A |  | 
0 | 5 | 5
2 |  | 8
C |  | 
6 | 6 | 12
6 |  | 11
B |  | 
6 | 5 | 11
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
12 | 3 | 15
11 |  | 13
D |  | 
11 | 2 | 13
17 |  | 21
G |  | 
17 | 4 | 21
Precedence Diagram Backward Pass
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2
LFA = MIN(LSC - SSAC + DA , LSB - FSAB )
LSA = LFA - DA

## Slide 41
0 |  | 5
A |  | 
0 | 5 | 5
2 |  | 8
C |  | 
6 | 6 | 12
6 |  | 11
B |  | 
6 | 5 | 11
13 |  | 14
F |  | 
14 | 1 | 15
12 |  | 15
E |  | 
12 | 3 | 15
11 |  | 13
D |  | 
11 | 2 | 13
17 |  | 21
G |  | 
17 | 4 | 21
Critical Path
FS 1
SS 2
FS
FS -1
FF2
SF (1,2)
ZZ(2,6)
FS 2

## Slide 42: Gantt Chart
A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21